## Blankett
Project number/project/site |  |  | Date | Prepared by
Construction part | Task
Starting date | Finnish date | Hours/size of team
Work preparation based on the following preconditions and documentation
Drawings/specifications etc.
Requirements - Instructions from manufacturer/supplier
www.ByggAi.se - other information - cost estimate
Starting conditions - checks before start - safety and working environment
Risk analysis & handeling - Technology, environment etc. |  |  | Remedy
Description of working method - logistics and materials handeling
Staffing - who will do the work?
Materials and auxiliary materials - fasteners and oil---
Assistive devices - machines, tools, equipment, temporary devices …
Items to check - Quality - Environment - Safety
Residual products - waste management and residual products
Coordination - with other professions and sub-contractors
"Relay change" - next occupational group / protective measures / cleaning
Follow-up and feedback
Signing
Date | Note-taker
Participants/signatures
2020-08-01
Risk of falling
Dangerous subst
Heavy materials
Sundry:
Fire risk
Planning
Work preparation
During work
Follow-up